## Sheet1
l | Task | Description | Dependencies | Deliverables | Responsibility | Start by | Due by
| Mass Audit | Do audit of mass budget, including additional flight hardware and (possibly) balloon. Aim for 10% accuracy | Selection and finalisation of all balloon flight hardware | Spreadsheet with mass breakdown
| Flight Stress Analyses | Make sure all suspension points on the satellite can withstand mechanical stresses as specified by CASA101 | None | Theoretical report with recommendations
| ADS-B Transponder | Source and/or design an ADS-B transponder that conforms to CASA reqs and is as light/small/low power as possible | None | Spreadsheet with comparisons of options and source for buying
| Ballast | Research if Ballast is needed for BLUEsat balloon flight | None | Yes/no. If yes, explanation of why
| Termination Device | Design device to terminate flight. Device will have to sever mechanical connection between BLUEsat and Balloon. CASA requires two independent means of control (CONFIRM THIS). Suggested means are RF Link Static Timer Altitude Sensor | None | All design files for device and copies of working prototype.
| Recovery Location | Determine a way to find the satellite once it has landed. Bigger/more expensive payloads use an over-head plane to visually inspect the area. Suggested means include RF Beacon GPS with mobile phone transmission | None | All design files for proposed system and copies of working prototype
| Parachute Seperation | Design device which seperates BLUEsat from the Parachute either after landing, or just before landing. This is necessary to stop from the parachute dragging the satellite across the ground. Note that HAM RF links probably won't be accesssable due to lack of line of sight. Suggested means are 3G link Tension sensor Termination over Ham RF 10m before landing Altitude Sensor | None | All design files for proposed system and copies of working prototype
| Landing Location | Use wind models + data to create probability distribution of where BLUEsat is likely to land | None | Map with probability distribution, technical reports on methods used
| Recovery Plans | Based upon finite list of possible landing locations (lake, gorge, flat land etc) - generate a recovery plan for each situation | Landing Location | Documents documenting procedure for each case
| New Fastener Setup | Install new set of fasteners for PCB mounting. | None | All PCB fasteners installed.
| Antenna Support Design | Design a support to prevent damage to antenna due to wind fibration during flight. | None | All design files for proposed system and copies of working prototype
| Radio Mechanical Integration | Design and perform necessary modifications to incorperate new radios. | Arrival of new radios. | Design files and necessary structural modificaitons.
| Flight RF Input | Source RF module to use as input to Raspberry pi flight hardware computer Also design antenna necessary for design | None | Spreadsheet with comparisons of options and source for buying
| APRS | Source APRS module suitable to use as post-flight locator. APRS module needs to work via Ham radio bands, have a standalone battery. GPS module should also be sourced that is compatible. | None | Spreadsheet with comparisons of options and source for buying
| Flight hardware power supply | Find a power supply (non-rechargable) that is able to distribute power to all flight hardware (non BLUEsat) | Sourcing of all other flight hardware components | Spreadsheet with comparisons of options and source for buying